## Tabelle1
Task | Date | Duration in h | Description | Responsible
Initial discussion/planning | 2022-12-20 | 1.5 | Decide which project to implement, discuss administrative setup & timeline | Jonas Speiser, Vincent König
Setup of GitLab repository | 2022-12-20 | 1 | Initial setup of GitLab project and structure | Jonas Speiser
Draft timeline & responsibilities | 2022-12-23 | 2 | Distribute responsibilies (use case development etc.), decide technology stack, agree on timeline and meeting times | Jonas Speiser, Vincent König
Setup of project in IntelliJ | 2022-12-30 | 4 | Set up project in IntelliJ, draft architecture and structure, decide on naming convention etc. | Jonas Speiser, Vincent König
Initial setup of frontend | 2022-12-30 | 2 | Initialize vue.js for frontend implementation | Jonas Speiser, Vincent König
Setup of backend structure | 2022-12-31 | 6 | Set up first backend services (user, inserat, kauf etc.) | Jonas Speiser
Setup of frontend structure | 2022-12-31 | 5 | Set up first frontend views | Vincent König
Setup of docker | 2022-12-31 | 2 | Set up docker compose file for frontend, mongodb, backend, and NGINX | Jonas Speiser, Vincent König
Backend development | 2023-01-02 | 4 | Further develop backend structure & services | Jonas Speiser
Backend development | 2023-01-03 | 8 | Implement endpoints and methods for B2B use cases | Jonas Speiser, Vincent König
Backend development | 2023-01-06 | 5 | Further develop backend structure & services | Jonas Speiser
Validation | 2023-01-06 | 3 | Experiment with validation measures (validation in springboot, validation against json schema) | Vincent König
Frontend development | 2023-01-08 | 7 | Further develop frontend views, connect frontend to backend (axios) | Jonas Speiser, Vincent König
Additional requirements | 2023-01-11 | 4 | Initialize readme file, initialize postman collection | Jonas Speiser
Backend & frontend development | 2023-01-12 | 5 | Finalize backend structure for login/user registration service, further develop frontend views | Jonas Speiser, Vincent König
Backend development | 2023-01-13 | 5 | Implement user authentication in backend | Jonas Speiser
Backend & frontend development | 2023-01-14 | 4 | Finalize backend structure for matching service | Jonas Speiser
SSL authentification & GraphQL | 2023-01-15 | 5 | Implement SSL authentification with NginX, initialize GraphQL interface | Jonas Speiser
Frontend development | 2023-01-15 | 5 | Finalize frontend and implement Admin use case | Jonas Speiser, Vincent König
Additional requirements | 2023-01-15 | 5 | Create json files for batch input requirement in postman collection, continue readme file, crate diagram with archimate | Vincent König
Batch input & GraphQL | 2023-01-16 | 3 | Set up batch input functionality in backend, finalize GraphQL interface | Jonas Speiser
Additional requirements | 2023-01-16 | 2 | Finalize readme file and documentation | Jonas Speiser, Vincent König
Test | 2023-01-16 | 3 | Test implementation and decide presentation approach | Jonas Speiser, Vincent König